## Sheet1
| 900 | 900 | w/p
| 3 | 4 | pgs
| 2700 | 3600
abstract | 200 | 200 | 100 | 10
intro | 360 | 540 | 495 | 10
problem | 360 | 540 | 144 | 10
lit surv | 720 | 1080 | 1062 | 20
method | 360 | 540 | 415 | 10 | 50
plann | 700 | 700 |  | 10
ref |  |  |  | 10
writ+pres |  |  |  | 20
100

## Sheet2
Phase | Milestone | Sub-milestone | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Phase 1 | Approved research proposal | bar: Jan to Feb
Phase 2 | Chapter 1, 2 | bar: Mar to Apr
Introduction/Background | bar: Mar to Apr
Literature survey | bar: Mar to Apr
Chapter 3,4 | bar: Apr to May
Research design | bar: Apr to May
Methodology | bar: Apr to May
Final chapter 1-4 | bar: May
Phase 3 | Data Collection | bar: May to Jul
Set up experiments | bar: May to Jul
Conduct data collection | bar: May to Jul
Conduct initial analysis | bar: May to Jul
Decide and conduct additional experiments as needed | bar: May to Jul
Chapter 5 | bar: Jul to Aug
Results and initial analysis | bar: Jul to Aug
Chapter 6&7 | bar: Aug to Sep
Discussion of results | bar: Aug to Sep
Conclusions and recommendations | bar: Aug to Sep
Phase 4 | Final Report | bar: Sep
Internal & External examination | bar: Nov